## Read me
Value Lifecycle · VR Intake Workbook — Read me
How to use this workbook, and how each tab maps to the Value Lifecycle Platform.
Purpose | Capture what you learn in client meetings, then transcribe into the app — or import this whole file.
Colour key | Yellow cells = you fill in. Grey cells = auto-calculated (don't type over them). Header rows = fixed.
Dropdowns | Cells with a dropdown use the app's own pick-lists (solution profiles, study types, KPIs, currencies, statuses) so entries match the system.
Example row | The first data row of each table is a greyed-italic EXAMPLE of the format — overwrite it or delete it.
Provenance | Wherever you record a number, capture its Source / Period / Assumption / Confidence.
Importing | A study/track can be loaded straight from this file: npx tsx scripts/import-workbook.ts <file>.xlsx (add --dry-run to preview).
Before you import | Delete the greyed example row in each table (or add rows beneath it); keep the tab names and column headers unchanged.
Tab → App module
1. Track | Realization track header (origin, objectives, planned value)
2. Baselines | Validate/establish KPI baselines
3. Work packages | Work packages
4. Adoption plan | Adoption plan activities
5. KPI tracker | KPI targets + actuals by period
6. Benefits | Benefits — planned vs realized
7. Risks & issues | Track risk/issue register
8. QBR notes | Quarterly value review notes
9. Lessons | Lessons learned
Reference | KPI catalogue + per-profile drivers & levers

## Reference
Reference — KPI catalogue & profile prompts
Pick-list prompts from the app. Use these to fill the dropdowns and shape the conversation.
KPI key | KPI name | Unit | Direction | Discipline | Category
cost_savings | Estimated / realized cost savings | USD | HIGHER_IS_BETTER | VE | COST_SAVING
roi_pct | Return on investment | % | HIGHER_IS_BETTER | VE | COST_SAVING
payback_period | Payback period | months | LOWER_IS_BETTER | VE | COST_SAVING
revenue_uplift | Revenue uplift | USD | HIGHER_IS_BETTER | VR | REVENUE_UPLIFT
alternatives_generated | Alternatives generated | count | HIGHER_IS_BETTER | VE | OTHER
recommendations_accepted | Recommendations accepted | count | HIGHER_IS_BETTER | VE | OTHER
study_cycle_time | Study cycle time | days | LOWER_IS_BETTER | VE | TIME_SAVING
avg_roi | Average ROI per study | % | HIGHER_IS_BETTER | VE | COST_SAVING
on_time_implementation | On-time implementation | % | HIGHER_IS_BETTER | VR | SCHEDULE
adoption_rate | Adoption rate | % | HIGHER_IS_BETTER | VR | OTHER
task_utilization | Licence / capacity utilization | % | HIGHER_IS_BETTER | VR | COST_SAVING
time_to_value | Time-to-value | days | LOWER_IS_BETTER | VR | TIME_SAVING
dev_productivity | Developer productivity | index | HIGHER_IS_BETTER | VR | TIME_SAVING
onboarding_time | New-developer onboarding time | months | LOWER_IS_BETTER | VR | TIME_SAVING
realized_value | Realized value | USD | HIGHER_IS_BETTER | VR | COST_SAVING
net_variance | Planned vs realized variance | % | HIGHER_IS_BETTER | VR | OTHER
reports_delivered | Value reports / QBRs delivered | count | HIGHER_IS_BETTER | VR | OTHER
total_realized_value | Total realized value (portfolio) | USD | HIGHER_IS_BETTER | VR | COST_SAVING
template_reuse_rate | Template / plan reuse rate | % | HIGHER_IS_BETTER | VR | OTHER
schedule_impact_days | Schedule impact | days | LOWER_IS_BETTER | VE | SCHEDULE
lcc_reduction | Life-cycle cost reduction | USD | HIGHER_IS_BETTER | VE | COST_SAVING
reliability_uptime | Reliability / uptime | % | HIGHER_IS_BETTER | VR | RELIABILITY
unit_cost_reduction | Unit cost reduction | USD | HIGHER_IS_BETTER | VE | COST_SAVING
first_pass_yield | First pass yield | % | HIGHER_IS_BETTER | VR | QUALITY
mainframe_cost | Mainframe cost reduction (MLC / MSU) | USD | HIGHER_IS_BETTER | VE | COST_SAVING
mttr | Mean time to resolve (MTTR) | hours | LOWER_IS_BETTER | VR | RELIABILITY
job_success_rate | Job success rate | % | HIGHER_IS_BETTER | VR | RELIABILITY
sla_attainment | SLA attainment | % | HIGHER_IS_BETTER | VR | RELIABILITY
ticket_deflection | Ticket deflection rate | % | HIGHER_IS_BETTER | VR | COST_SAVING
first_contact_resolution | First-contact resolution | % | HIGHER_IS_BETTER | VR | QUALITY

## _Lists (hidden)
SolutionProfiles | StudyTypes | CostItemKind | BenefitCategory | FunctionKind | RecommendationStatus | YesNo | Currencies | KpiNames | WorkPackageStatus | RiskStatus | Health | Confidence | Scale | TrackOrigin | ArtifactType | LessonCat
automation | Adoption & value-realization study | CAPEX | COST_SAVING | BASIC | PROPOSED | Yes | USD | Estimated / realized cost savings | NOT_STARTED | OPEN | GREEN | High | 1 | STANDALONE (existing software) | EXPECTED_BENEFIT | what_worked
mainframe | Automation value study | OPEX | REVENUE_UPLIFT | SECONDARY | SHORTLISTED | No | ZAR | Return on investment | IN_PROGRESS | MITIGATING | AMBER | Medium | 2 | VE_HANDOVER (from a study) | SUCCESS_CRITERION | what_to_change
serviceops | Availability & resilience review | ONE_OFF | RISK_REDUCTION |  | ACCEPTED |  | EUR | Payback period | BLOCKED | CLOSED | RED | Low | 3 |  | BASELINE | recommendation_for_ve
reseller | Build-vs-buy business case | RECURRING | TIME_SAVING |  | REJECTED |  | GBP | Revenue uplift | DONE | ACCEPTED |  |  | 4 |  | KPI
| Capacity & cost forecasting study | BENEFIT | QUALITY |  | DEFERRED |  | AUD | Alternatives generated |  |  |  |  | 5 |  | RISK
| Cloud migration / modernization TCO case |  | SCHEDULE |  |  |  | NGN | Recommendations accepted
| Competitive displacement / TCO case |  | RELIABILITY |  |  |  | KES | Study cycle time
| Consolidation case (tool / licence) |  | OTHER |  |  |  | BWP | Average ROI per study
| Continuous optimization / cost case | [6 empty] | On-time implementation
| Cost-optimization study | [6 empty] | Adoption rate
| ITSM value / TCO study | [6 empty] | Licence / capacity utilization
| Managed-service (MSP) migration case | [6 empty] | Time-to-value
| Proof-of-value (PoV) outcome study | [6 empty] | Developer productivity
| Renewal & expansion case | [6 empty] | New-developer onboarding time
| ROI / TCO business case | [6 empty] | Realized value
| SaaS migration case | [6 empty] | Planned vs realized variance
| Security & compliance risk-reduction case | [6 empty] | Value reports / QBRs delivered
| Self-service deflection study | [6 empty] | Total realized value (portfolio)
| Value realisation & optimisation study | [6 empty] | Template / plan reuse rate
Schedule impact
Life-cycle cost reduction
Reliability / uptime
Unit cost reduction
First pass yield
Mainframe cost reduction (MLC / MSU)
Mean time to resolve (MTTR)
Job success rate
SLA attainment
Ticket deflection rate
First-contact resolution

## 1. Track
1 · Track
Realization track header → maps to the app's New realization track (or the VE → VR handover).
Client / account
Track title | ITSM Platform Displacement — Value Realization
Origin | Handover from VE study
Source study code (if handover)
Solution profile | serviceops
VRM (owner)
Objectives | Realise the displacement business case: stand up the target platform, migrate off the incumbent, and prove the ~$630K/yr net platform saving while improving MTTR, deflection and SLA.
Success criteria | Incumbent fully decommissioned on plan; net annual TCO saving ≥ $630K evidenced; MTTR ≤ 4.0h; deflection ≥ 35%; zero consumption / true-up overages post-cutover.
Planned value | 630000
Currency | USD
Start date | 2027-01-15
Target date | 2027-12-31

## 2. Baselines
2 · Baseline & measurement
Validate baselines (handover) or establish them from the live deployment (standalone).
KPI (pick) | KPI key (auto) | Baseline value | Unit (auto) | Data source | Frequency | Owner | Validated / established?
Mean time to resolve (MTTR) | mttr | 6.5 | hours | Incumbent ITSM reports | Monthly | IT Operations | yes
SLA attainment | sla_attainment | 92 | % | Incumbent SLA reports | Monthly | Service Owner | yes
Ticket deflection rate | ticket_deflection | 18 | % | Portal analytics | Monthly | Service Owner | yes
First-contact resolution | first_contact_resolution | 61 | % | ITSM | Monthly | Service Desk Lead | yes

## 3. Work packages
3 · Work packages
From accepted recommendations, or defined directly for a standalone track.
Name | Description | Owner | Start | Due | Status
Stand up target platform (Kubernetes, in-country) | Deploy ITSM + AIOps on private cloud for data residency | Platform Engineering | 2027-01-15 | 2027-03-15 | IN_PROGRESS
Migrate CMDB & discovery (200k–800k items) | ETL + discovery re-baseline; index tuning for large item loads | CMDB Lead | 2027-02-01 | 2027-05-15 | NOT_STARTED
Migrate ITSM processes (incident/request/change/problem) | Configure workflows; parallel run against the incumbent | ITSM Lead | 2027-03-01 | 2027-06-30 | NOT_STARTED
Rebuild priority integrations (iPaaS / REST) | Top 10 integrations first; retire incumbent connectors | Integration Lead | 2027-03-15 | 2027-06-30 | NOT_STARTED
Cutover & decommission incumbent | Domain-by-domain cutover aligned to renewal; contract exit | Programme Manager | 2027-07-01 | 2027-09-30 | NOT_STARTED

## 4. Adoption plan
4 · Adoption plan
Who's impacted, training, comms, champions — value comes from use.
Activity | Audience / who's impacted | Owner | Due | Status
GenAI-assistant + modern-workplace training | All fulfillers & end users | Enablement | 2027-04-15 | NOT_STARTED
Champion network across service teams | Team leads | Service Owner | 2027-04-01 | IN_PROGRESS
Self-service / virtual-agent adoption push | End users | Comms | 2027-05-01 | NOT_STARTED

## 5. KPI tracker
5 · KPI tracker
Targets + actuals by period. Attainment auto-calcs vs baseline → target.
KPI (pick) | KPI key (auto) | Baseline | Target | Unit (auto) | Period | Actual | Attainment % (auto)
Mean time to resolve (MTTR) | mttr | 6.5 | 4 | hours | 2027-03-31 | 5.6
Mean time to resolve (MTTR) | mttr | 6.5 | 4 | hours | 2027-06-30 | 4.9
Ticket deflection rate | ticket_deflection | 18 | 35 | % | 2027-03-31 | 24
Ticket deflection rate | ticket_deflection | 18 | 35 | % | 2027-06-30 | 29
SLA attainment | sla_attainment | 92 | 98 | % | 2027-06-30 | 95
First-contact resolution | first_contact_resolution | 61 | 75 | % | 2027-06-30 | 67

## 6. Benefits
6 · Benefits — planned vs realized
Realized rolls up to the track & portfolio in the app.
Benefit | Category | Planned value | Realized value | Variance (auto)
Platform TCO reduction vs the incumbent (net, annualised) | COST_SAVING | 630000 | 160000
Eliminated consumption / true-up surprises | RISK_REDUCTION | 0 | 0

## 7. Risks & issues
7 · Risks & issues
Risks to realizing value.
Risk / issue | Likelihood (1–5) | Impact (1–5) | Score (auto) | Mitigation | Status
CMDB migration index performance on large item loads | 3 | 3 |  | Index tuning; batch loads; discovery re-baseline | OPEN
Integration rebuild backlog slows cutover | 3 | 3 |  | Prioritise top-10 integrations; iPaaS first | OPEN
Adoption lag vs the familiar incumbent UI | 2 | 3 |  | GenAI assistant UX; champions; training | MITIGATING
Incumbent decommission slips past renewal date | 2 | 4 |  | Domain-by-domain cutover; procurement-led exit plan | OPEN

## 8. QBR notes
8 · QBR / value review notes
Reconcile realized value vs the business case.
Review date
Attendees
Realized vs planned (summary) | One quarter into realization ~$160K of the $630K annual net saving is banked (incumbent operations-mgmt & AI consumption already off the bill). MTTR down 6.5→4.9h and deflection 18→29% as AIOps and the GenAI assistant come online.
Wins | GenAI assistant live; AIOps cut alert noise ~95%; first two service domains cut over; no consumption overages since migration started.
Risks / blockers | CMDB migration index performance and the integration-rebuild backlog are the critical path to full decommission.
Renewal / expansion signal | Incumbent renewal exit on track; strong signal to extend the platform to security operations and HR service delivery later.
Actions & owners | Finish CMDB cutover — CMDB Lead; prioritise top-10 integrations — Integration Lead; book executive QBR — CSM

## 9. Lessons
9 · Lessons learned
Feed improvements back into the VE templates & playbooks.
Category | Lesson | Recommendation for next time
what_worked | Coexistence dual-run removed cutover risk and protected SLAs | Reuse the phased, domain-by-domain displacement playbook
watch_out | Integration rebuild took longer than the licence migration itself | Start iPaaS/REST integration mapping in week 1, before ITSM config