## Read me
Value Lifecycle · VR Intake Workbook — Read me
How to use this workbook, and how each tab maps to the Value Lifecycle Platform.
Purpose | Capture what you learn in client meetings, then transcribe into the app — or import this whole file.
Colour key | Yellow cells = you fill in. Grey cells = auto-calculated (don't type over them). Header rows = fixed.
Dropdowns | Cells with a dropdown use the app's own pick-lists (solution profiles, study types, KPIs, currencies, statuses) so entries match the system.
Example row | The first data row of each table is a greyed-italic EXAMPLE of the format — overwrite it or delete it.
Provenance | Wherever you record a number, capture its Source / Period / Assumption / Confidence.
Importing | A study/track can be loaded straight from this file: npx tsx scripts/import-workbook.ts <file>.xlsx (add --dry-run to preview).
Before you import | Delete the greyed example row in each table (or add rows beneath it); keep the tab names and column headers unchanged.
Tab → App module
1. Track | Realization track header (origin, objectives, planned value)
2. Baselines | Validate/establish KPI baselines
3. Work packages | Work packages
4. Adoption plan | Adoption plan activities
5. KPI tracker | KPI targets + actuals by period
6. Benefits | Benefits — planned vs realized
7. Risks & issues | Track risk/issue register
8. QBR notes | Quarterly value review notes
9. Lessons | Lessons learned
Reference | KPI catalogue + per-profile drivers & levers

## Reference
Reference — KPI catalogue & profile prompts
Pick-list prompts from the app. Use these to fill the dropdowns and shape the conversation.
KPI key | KPI name | Unit | Direction | Discipline | Category
cost_savings | Estimated / realized cost savings | USD | HIGHER_IS_BETTER | VE | COST_SAVING
roi_pct | Return on investment | % | HIGHER_IS_BETTER | VE | COST_SAVING
payback_period | Payback period | months | LOWER_IS_BETTER | VE | COST_SAVING
revenue_uplift | Revenue uplift | USD | HIGHER_IS_BETTER | VR | REVENUE_UPLIFT
alternatives_generated | Alternatives generated | count | HIGHER_IS_BETTER | VE | OTHER
recommendations_accepted | Recommendations accepted | count | HIGHER_IS_BETTER | VE | OTHER
study_cycle_time | Study cycle time | days | LOWER_IS_BETTER | VE | TIME_SAVING
avg_roi | Average ROI per study | % | HIGHER_IS_BETTER | VE | COST_SAVING
on_time_implementation | On-time implementation | % | HIGHER_IS_BETTER | VR | SCHEDULE
adoption_rate | Adoption rate | % | HIGHER_IS_BETTER | VR | OTHER
task_utilization | Licence / capacity utilization | % | HIGHER_IS_BETTER | VR | COST_SAVING
time_to_value | Time-to-value | days | LOWER_IS_BETTER | VR | TIME_SAVING
dev_productivity | Developer productivity | index | HIGHER_IS_BETTER | VR | TIME_SAVING
onboarding_time | New-developer onboarding time | months | LOWER_IS_BETTER | VR | TIME_SAVING
realized_value | Realized value | USD | HIGHER_IS_BETTER | VR | COST_SAVING
net_variance | Planned vs realized variance | % | HIGHER_IS_BETTER | VR | OTHER
reports_delivered | Value reports / QBRs delivered | count | HIGHER_IS_BETTER | VR | OTHER
total_realized_value | Total realized value (portfolio) | USD | HIGHER_IS_BETTER | VR | COST_SAVING
template_reuse_rate | Template / plan reuse rate | % | HIGHER_IS_BETTER | VR | OTHER
schedule_impact_days | Schedule impact | days | LOWER_IS_BETTER | VE | SCHEDULE
lcc_reduction | Life-cycle cost reduction | USD | HIGHER_IS_BETTER | VE | COST_SAVING
reliability_uptime | Reliability / uptime | % | HIGHER_IS_BETTER | VR | RELIABILITY
unit_cost_reduction | Unit cost reduction | USD | HIGHER_IS_BETTER | VE | COST_SAVING
first_pass_yield | First pass yield | % | HIGHER_IS_BETTER | VR | QUALITY
mainframe_cost | Mainframe cost reduction (MLC / MSU) | USD | HIGHER_IS_BETTER | VE | COST_SAVING
mttr | Mean time to resolve (MTTR) | hours | LOWER_IS_BETTER | VR | RELIABILITY
job_success_rate | Job success rate | % | HIGHER_IS_BETTER | VR | RELIABILITY
sla_attainment | SLA attainment | % | HIGHER_IS_BETTER | VR | RELIABILITY
ticket_deflection | Ticket deflection rate | % | HIGHER_IS_BETTER | VR | COST_SAVING
first_contact_resolution | First-contact resolution | % | HIGHER_IS_BETTER | VR | QUALITY

## _Lists (hidden)
SolutionProfiles | StudyTypes | CostItemKind | BenefitCategory | FunctionKind | RecommendationStatus | YesNo | Currencies | KpiNames | WorkPackageStatus | RiskStatus | Health | Confidence | Scale | TrackOrigin | ArtifactType | LessonCat
automation | Adoption & value-realization study | CAPEX | COST_SAVING | BASIC | PROPOSED | Yes | USD | Estimated / realized cost savings | NOT_STARTED | OPEN | GREEN | High | 1 | STANDALONE (existing software) | EXPECTED_BENEFIT | what_worked
mainframe | Automation value study | OPEX | REVENUE_UPLIFT | SECONDARY | SHORTLISTED | No | ZAR | Return on investment | IN_PROGRESS | MITIGATING | AMBER | Medium | 2 | VE_HANDOVER (from a study) | SUCCESS_CRITERION | what_to_change
serviceops | Availability & resilience review | ONE_OFF | RISK_REDUCTION |  | ACCEPTED |  | EUR | Payback period | BLOCKED | CLOSED | RED | Low | 3 |  | BASELINE | recommendation_for_ve
reseller | Build-vs-buy business case | RECURRING | TIME_SAVING |  | REJECTED |  | GBP | Revenue uplift | DONE | ACCEPTED |  |  | 4 |  | KPI
| Capacity & cost forecasting study | BENEFIT | QUALITY |  | DEFERRED |  | AUD | Alternatives generated |  |  |  |  | 5 |  | RISK
| Cloud migration / modernization TCO case |  | SCHEDULE |  |  |  | NGN | Recommendations accepted
| Competitive displacement / TCO case |  | RELIABILITY |  |  |  | KES | Study cycle time
| Consolidation case (tool / licence) |  | OTHER |  |  |  | BWP | Average ROI per study
| Continuous optimization / cost case | [6 empty] | On-time implementation
| Cost-optimization study | [6 empty] | Adoption rate
| ITSM value / TCO study | [6 empty] | Licence / capacity utilization
| Managed-service (MSP) migration case | [6 empty] | Time-to-value
| Proof-of-value (PoV) outcome study | [6 empty] | Developer productivity
| Renewal & expansion case | [6 empty] | New-developer onboarding time
| ROI / TCO business case | [6 empty] | Realized value
| SaaS migration case | [6 empty] | Planned vs realized variance
| Security & compliance risk-reduction case | [6 empty] | Value reports / QBRs delivered
| Self-service deflection study | [6 empty] | Total realized value (portfolio)
| Value realisation & optimisation study | [6 empty] | Template / plan reuse rate
Schedule impact
Life-cycle cost reduction
Reliability / uptime
Unit cost reduction
First pass yield
Mainframe cost reduction (MLC / MSU)
Mean time to resolve (MTTR)
Job success rate
SLA attainment
Ticket deflection rate
First-contact resolution

## 1. Track
1 · Track
Realization track header → maps to the app's New realization track (or the VE → VR handover).
Client / account
Track title | Managed multi-tenant ITSM — Value Realization (incumbent displacement)
Origin | Handover from VE study
Source study code (if handover)
Solution profile | serviceops
VRM (owner)
Objectives | Realise the displacement business case: stand up the ring-fenced multi-tenant platform on the partner's managed cloud, migrate the MSP off the incumbent tenant-by-tenant, and prove the ~$0.6M/yr net value while improving SLA, deflection and MTTR.
Success criteria | Incumbent decommissioned on plan; net annual value ≥ $0.6M evidenced; SLA ≥ 98%; deflection ≥ 35%; MTTR ≤ 4.5h; zero cross-tenant data incidents; platform fully partner-operated.
Planned value | 600000
Currency | USD
Start date | 2027-01-15
Target date | 2027-10-31

## 2. Baselines
2 · Baseline & measurement
Validate baselines (handover) or establish them from the live deployment (standalone).
KPI (pick) | KPI key (auto) | Baseline value | Unit (auto) | Data source | Frequency | Owner | Validated / established?
SLA attainment | sla_attainment | 90 | % | Incumbent / service reports | Monthly | MSP Service Mgmt | yes
Mean time to resolve (MTTR) | mttr | 7.5 | hours | Incumbent reports | Monthly | MSP Operations | yes
Ticket deflection rate | ticket_deflection | 12 | % | Portal analytics | Monthly | MSP Service Mgmt | yes
First-contact resolution | first_contact_resolution | 58 | % | Incumbent | Monthly | Service Desk Lead | yes

## 3. Work packages
3 · Work packages
From accepted recommendations, or defined directly for a standalone track.
Name | Description | Owner | Start | Due | Status
Stand up ring-fenced multi-tenant platform (partner cloud) | Provision the isolated ITSM instance on the partner's managed cloud; multi-tenancy & data isolation | Platform partner — Platform Eng | 2027-01-15 | 2027-03-15 | IN_PROGRESS
Configure ITSM processes + self-service portal | Incident/request/change/problem/knowledge; per-tenant SLAs & catalogues | Platform partner — Delivery | 2027-02-01 | 2027-04-30 | NOT_STARTED
Deploy digital workplace + GenAI virtual agent | Virtual agent, knowledge grounding and modern self-service across tenants | Platform partner — Delivery | 2027-03-01 | 2027-05-15 | NOT_STARTED
Rebuild integrations (directory/SSO, email, monitoring) | Top integrations first; iPaaS/REST connectors | Platform partner — Integration | 2027-03-15 | 2027-06-30 | NOT_STARTED
Migrate tenants off the incumbent (phased, per-tenant) | Tenant-by-tenant data & workflow migration with parallel run | Partner + MSP | 2027-04-01 | 2027-09-15 | NOT_STARTED
Cutover & decommission the incumbent; operate handover | Final cutover, decommission the incumbent, transition to partner managed-operate | Platform partner — Delivery Lead | 2027-09-15 | 2027-10-31 | NOT_STARTED

## 4. Adoption plan
4 · Adoption plan
Who's impacted, training, comms, champions — value comes from use.
Activity | Audience / who's impacted | Owner | Due | Status
Analyst training & champions (new platform vs incumbent) | MSP service-desk analysts | MSP Service Mgmt | 2027-04-15 | IN_PROGRESS
GenAI virtual-agent + self-service enablement | End-users across tenants | Partner / MSP Enablement | 2027-05-01 | NOT_STARTED
Per-tenant onboarding playbook | New end-customer tenants | Platform partner — Delivery | 2027-04-01 | NOT_STARTED

## 5. KPI tracker
5 · KPI tracker
Targets + actuals by period. Attainment auto-calcs vs baseline → target.
KPI (pick) | KPI key (auto) | Baseline | Target | Unit (auto) | Period | Actual | Attainment % (auto)
Mean time to resolve (MTTR) | mttr | 7.5 | 4.5 | hours | 2027-03-31 | 6.6
Mean time to resolve (MTTR) | mttr | 7.5 | 4.5 | hours | 2027-06-30 | 5.3
Ticket deflection rate | ticket_deflection | 12 | 35 | % | 2027-03-31 | 18
Ticket deflection rate | ticket_deflection | 12 | 35 | % | 2027-06-30 | 26
SLA attainment | sla_attainment | 90 | 98 | % | 2027-06-30 | 95
First-contact resolution | first_contact_resolution | 58 | 75 | % | 2027-06-30 | 64

## 6. Benefits
6 · Benefits — planned vs realized
Realized rolls up to the track & portfolio in the app.
Benefit | Category | Planned value | Realized value | Variance (auto)
Net platform value vs the incumbent (annualised) | COST_SAVING | 600000 | 140000
Platform-ops FTE redeployed to billable delivery | TIME_SAVING | 320000 | 80000
Eliminated self-hosting & patching risk | RISK_REDUCTION | 0 | 0

## 7. Risks & issues
7 · Risks & issues
Risks to realizing value.
Risk / issue | Likelihood (1–5) | Impact (1–5) | Score (auto) | Mitigation | Status
Tenant migration complexity slows cutover | 3 | 3 |  | Phased per-tenant migration; parallel run; ETL tooling | OPEN
Cross-tenant isolation / data-residency assurance | 2 | 5 |  | Ring-fenced instance; strict isolation; partner-managed; data-residency controls | MITIGATING
Analyst adoption lag vs the incumbent | 3 | 3 |  | GenAI virtual-agent UX; training; champions | OPEN
Integration rebuild backlog | 3 | 3 |  | Prioritise top-N integrations; iPaaS first | OPEN

## 8. QBR notes
8 · QBR / value review notes
Reconcile realized value vs the business case.
Review date
Attendees
Realized vs planned (summary) | One quarter into realization ~$140k of the $600k annual net value is banked — first tenant waves migrated, incumbent self-hosting partly retired. MTTR 7.5→5.3h and deflection 12→26% as platform automation and the GenAI virtual agent come online.
Wins | Ring-fenced multi-tenant instance live; GenAI self-service in pilot; first tenant waves cut over with no SLA breach; partner now operating the platform.
Risks / blockers | Remaining tenant migration waves and the integration backlog are the critical path to full incumbent decommission.
Renewal / expansion signal | Strong appetite for Phase 2 (AIOps + Discovery/CMDB) and for onboarding more end-customer tenants — expansion of both the MSP's value and partner ARR.
Actions & owners | Complete tenant migration waves — partner + MSP; finish directory/SSO & monitoring integrations — partner Integration; stand up quarterly value dashboard — partner CSM

## 9. Lessons
9 · Lessons learned
Feed improvements back into the VE templates & playbooks.
Category | Lesson | Recommendation for next time
what_worked | Phased, tenant-by-tenant migration with parallel run protected live SLAs | Reuse the per-tenant migration & onboarding playbook for future MSP moves
watch_out | Integration rebuild took longer than the ITSM configuration | Start directory/SSO and monitoring integration mapping in week 1